## Sheet1
IR Meeting Room Display |  | Legend
Deveoplers - Charlie Coyle, David Flynn |  | ARDUINO |  |  | ANDROID |  |  | OTHER |  |  | Documentation
|  | March | [20 empty] | April
|  | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7
Task Description | Assigned To | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
LCD screen wiring and scripting | Charlie | bar: March 11 M to March 15 F
XMAL interface implementation | David | bar: March 11 M to March 14 T
IR receiver installation/testing | Charlie | bar: March 18 M to March 22 F
IR Blaster accessing/testing | David | bar: March 15 F; March 18 M to March 22 F
Create timer function | Charlie | bar: March 25 M to March 27 W
Encode and decode info into IR patterns | David | bar: March 25 M to March 27 W
Create interrupt for cancelation | Charlie | bar: March 28 T to March 29 F
Create cancel button | David | bar: March 28 T to March 29 F
Test devices together | Charlie/David | bar: March 31 S to April 2 T
Fix issues | Charlie/David | bar: April 3 W to April 5 F
Document proccess | Charlie/David